## EXAMPLE 1-Page PMP
SR 3 Freight Corridor - New Alignment | [5 empty] | Project Management Plan | [8 empty] | Revision: 2021 March 1st DRAFT
Project Description |  |  |  | Project Limits |  |  | Project Budget [TEIS] |  |  |  |  | Reference Section
This project will construct a new alignment and two new connections to the existing State Route 3 in the vicinity of Lake Flora Rd in Kitsap County and State Route 302 in Mason County. The existing State Route 3 will become a Business Loop. This project originally began as a Mason County Project, with a draft environmental document prepared in 2001. In 2007, WSDOT took responsibility for the project and began community outreach and selecting preferred connection alternatives, as well as selecting an alignment. In 2011, an Environmental Assessment was funded and completed, but did not receive FONSI Approval as there was no construction funding identified. In 2017, the project was funded again through Connecting Washington, and a project summary was approved in the summer of 2019. |  |  |  | Olympic Region - Kitsap and Mason County BMP: 22.81 EMP: 29.49 |  |  | Phase |  |  | $ | % | Go to these locations to find specific guidance/information
[7 empty] | Preliminary Engineering |  |  | 4340253 | 6.487%
[7 empty] | Right of Way |  |  | 13958919 | 20.86% |  |  | (Primary location is the Port Orchard PEO "G" Drive)
[7 empty] | Construction |  |  | 48610828 | 72.65% | Risk Matrix |  | G:\2DesignPS&E\SR003 Freight Corridor - New Alignment\7.00 Design\7.08 Risk
[7 empty] | Total Project |  |  | 66910000 | 100% | Production Schedule |  | G:\2DesignPS&E\SR003 Freight Corridor - New Alignment\3.00 Schedule\3.01 Project Schedule
Change Mangement Plan
[7 empty] | Budget Request |  |  |  |  | Project Financials |  | G:\2DesignPS&E\SR003 Freight Corridor - New Alignment\2.00 Accounting
[7 empty] | Date | Phase | Status | Amount | % INCR | Communication Plan |  | G:\XL3107\Communication Plan
[12 empty] | SOW Agreements |  | G:\XL3107\Project Communication\Scope of Work Agreements
|  |  |  | Fund Source |  | CWA | [5 empty] | Full Estimates |  | G:\XL3107\Estimates
|  |  |  | Work Order |  | XL6043 | [5 empty] | Project Management Plan |  | G:\Project Management\Project Management Plans\SR3
|  |  |  | PIN |  | 300344E
|  |  |  | WIN |  | C00344E
Current Management Team Mission |  |  |  | Milestones | [6 empty] | Project Team |  |  |  | Scope of Work Expenditures
Manage a multi-disciplinary team of WSDOT and Consultant staff to reach key milestones that require strong coordination on both Project Develeopment and Schedule; including Environmental, Hydraulic and Right of Way activities. These project deliverables paired with multiple local agency and private developer projects require a high level of care and attention to detail in both communications and planning, which has been ongoing through check-in meetings and formal WSDOT Procedures. All of these activities are managed in bi-weekly management team meetings and weekly design team meetings. |  |  |  | Activity ID | Activity Name |  |  | Date |  |  | Project Engineer |  | Lone Moody |  | Office | Spent
|  |  |  | MS-0100 | Begin Preliminary Engineering |  |  | 2019-05-01 |  |  | Asst Project Engineer |  | Andy Larson |  | HQ Geotech
|  |  |  | 295 | Project Summary Complete |  |  | 2020-10-27 |  |  | Project Manager |  |  |  | OR Traffic
|  |  |  | EN3460 | Discipline Reports Complete* |  |  | 2021-05-01 |  |  | Design Team Leader |  | Kyle Cornwell |  | OR EHS
|  |  |  | 1130 | Record of Survey Complete* |  |  | 2021-06-30 |  |  | Designer-E2 |  | Erika Parsons |  | OR Plans
|  |  |  | EP2410 | Environmental Permits Received |  |  | 2022-11-02 |  |  | Consultant PM |  | Mark Yand |  | HQ ROW Office
Stakeholders |  |  |  | A1310 | Limited Access Hearing |  |  | 2022-07-18 |  |  | Environmental Lead |  | Victoria Book |  | HQ Hydraulics
Kitsap and Mason County Officials | Mason County PUD |  |  | RW2130 | R/W Appraisals Complete |  |  | 2022-10-23 |  |  | Consultant ENV Lead |  | Linda Amato |  | OR Utilities
Altabrook and Belwood Neighborhoods | Department of Fish & Wildlife |  |  | RW2130 | R/W Certification |  |  | 2023-10-18 |  |  | Consultant Design Manager |  | Mallory Wilde |  | OR Materials
Boneville Power Administration | Local legistators |  |  | MS0150 | Advertisement Date |  |  | 2023-12-18 | [6 empty] | HQ Environmental
Port of Bremerton | City of Bremerton |  |  | PSE7440 | Contract Award |  |  | 2024-01-22 | [6 empty] | Parametrix | 42%
E.E. Overton | Rainier Concepts |  |  | 2595 | Contract Execution |  |  | 2024-02-23
Skokomish Tribe | Suquamish Tribe |  |  | 2695 | Final Contract Completion |  |  | 2026-01-21
Squaxin Tribe | North Mason School District |  |  |  | *schedule coordination ongoing
The Church of Jesus Christ LDS - Belfair | Peninsula RTPO |  |  | PE Phase Cost Estimate
Active Coordination |  |  |  | Group |  |  |  | Amount
WSDOT Dynamic Warning Signs and Compact Roundabout - SR 3 and Lake Flora Rd |  |  |  | Parametrix and Subconsultants - Agreement |  |  |  | 2522995
Skokomish Tribe SR 3 Roundabout and Developments |  |  |  | Overhead |  |  |  | 0
E.E. Overton Forestry Road System |  |  |  | HQ Geotech |  |  |  | Pending SOWA
Puget Sound Industrial Center Loop Roads |  |  |  | OR Traffic |  |  |  | Pending SOWA
Mason County Log Yard Road Extension |  |  |  | OR EHS |  |  |  | Pending SOWA
Mason County Romance Hill Road Extension |  |  |  | Roadside Restoration |  |  |  | Pending SOWA
Mason County Sewer Main Extension |  |  |  | OR Plans |  |  |  | Pending SOWA
|  |  |  | HQ ROW Office |  |  |  | Pending SOWA
Potential Risks (See Risk Matrix for Comprehensive Information) |  |  |  | HQ Hydraulics |  |  |  | Pending SOWA
Risk | Schedule Impact |  | Budget Impact | OR Utilities |  |  |  | Pending SOWA
Alta Road Vic. Parcel Acquisiton | 9 mos. |  | 1000000 | OR Materials |  |  |  | Pending SOWA
Developer Coordination | 15 mos. |  | 800000 | Area 2 Maintenance |  |  |  | Pending SOWA
Issues with Property Acquisition | 9 mos. |  | 1000000 | Port Orchard PEO |  |  |  | Pending SOWA
Minor Opportunities (see CRA) | 4 mos. |  | 2000000 | HQ Environmental |  |  |  | Pending SOWA
|  |  |  | TOTAL |  |  |  | 4340253
Endorsed by Project Development Engineer on: PENDING |  | Note: This PMP must be placed in each team member office and updated when any data element is revised. Pictures are alternated with project maps, current site status or team/ team member successes.
Critical Success Factors
ONE-PAGE PMP EXAMPLE ONLY
EXAMPLE